## TASK LIST
Hour | Activities | Responsible Party | Completed
120 | Activate Emergency Operations Plan
120 | Activate ESRI Surge licenses- gather info for surge licenses
120 | Conduct pre-landfall readiness conference call with departments
120 | Create fresh Galveston County SITREP doc to begin monitoring approaching storm.
120 | Early Planning with field Departments and resources
120 | Evaluate and determine EOC Readiness Level
120 | Provide public information updates through PIO using multi-media
108 | Contact Purchasing/Auditor to implement Emergency P-Card policy; prepare standby POs
108 | Continue conference calls at pre-determined times with NWS, local, regional and state partners
108 | Decide who is activating and notify them
108 | Request disaster codes and payroll plans
108 | Ensure all county facilities and departments have executed their hurricane preparation plans and are prepared for landfall
108 | Prepare EOC, phone bank, and bunk rooms for activation
108 | Review damage assessment plans
108 | Review re-entry plans with Galveston, Jamaica Beach, Bayou Vista, Tiki Island and Hitchcock
108 | Schedule Decision-Makers Conference Call/Meeting if necessary
108 | Submit Logistics Requests (STAR) in Web EOC as needed
96 | Activate Gulf Coast Center transportation assistance contract
96 | Activate SFHS basecamp plan; notify SFISD to begin coordination with school district and jurisdictions
96 | Assist EOC, Santa Fe High School caterers with logistical needs
96 | Begin conference calls with National Weather Service, local and state partners to assess threat.
96 | Conduct Decision-Makers meeting/conference call to determine hurricane evacuation timeline
96 | Crenshaw Elemetary/Middle School: Notify ISD 72 hrs prior to needed use
96 | Ensure communication lines in place with TDEM, utility companies and VOADs
96 | Ensure supplies for disinfection, snacks, water and hand sanitizers are ready for busses.
96 | Evaluate and determine EOC Readiness Level
96 | Inventory EOC supplies for activation (office, janitorial, nutrition etc…)
96 | Inventory supplies to use in refuges of last resort (cots, blankets, water, MREs)
96 | Notify contractors that standby contracts may be activated (catering, Debris services, emergency public information, equipment/personnel, buses, Santa Fe High School, etc.)
96 | Notify departments to prep their Tier 1-2 county employees of policies regarding emergencies
96 | Notify EOC staff of evacuation timeline and activation information (time to report for duty)
96 | Order additional restroom supplies,cleansers and toiletries as needed
96 | Order food and kitchen paper goods
96 | Place amateur radio group on standby if needed - GCECG
96 | Place volunteers on standby (embarkation, call center, etc)
96 | Provide regular public information updates to media partners
96 | Provide regular status updates to regional partners
96 | Put Search and Rescue Teams on standby
96 | Request additional resources through DDC as needed
96 | Submit STARs for busses, Texas Military Forces, ambusses and ambulances as needed
96 | Work with County Judge's office to prepare local state of disaster and request to governor for state/federal declarations
84 | Coordinate with ASPCA, Humane Society regarding animal rescue and sheltering post-landfall
84 | Create daily battle rhythm for meetings and Sit-Reps
84 | Crenshaw Elemetary/Middle School: Provide 6 portable restrooms, post-landfall
84 | Crenshaw Elemetary/Middle School: Provide accomodations (i.e. cots, pillows, blankets)
84 | Crenshaw Elemetary/Middle School: Provide certified electrician to assist w/ quick-connect connection
84 | Crenshaw Elemetary/Middle School: Provide meals
84 | Crenshaw Elemetary/Middle School: Transport a generator (connect via quick-connect) and fuel
84 | Determine location and details of county ride-out teams
84 | Monitor 2-1-1 data base for late entries; coordinate pickup of functional needs residents with GCHD
84 | Notify TDEM that shelters may be needed. Contact hotels if non-congregate care is needed.
84 | Prepare Incident Action Plan for first activation shift in EOC
84 | Send pre-evacuation news releases to media regarding fuel, pets, and evacuation supplies; post online
84 | Work with cities to ensure evacuation plans for long term care facilities are implemented
72 | Activate bus loading teams for points of embarkation
72 | Activate Core EOC staffing
72 | Begin disinfecting high touch areas in EOC frequently
72 | Notify access/functional needs populations of evacuation timeline for arriving at points of embarkation
72 | Continue relocation of staff and equipment to Santa Fe High School; provide logistical support as needed
72 | Coordinate potential ambulance needs with GCHD (CMOC, SETRAC)
72 | Coordinate shutdown and restart plans with Gulf Coast Water Authority and countywide MUDs, SUDs, etc.
72 | Coordinate various phases of evacuation with Law Enforcement, TranStar, TxDOT and other jurisdictions
72 | Coordinate with Bolivar Peninsula Special Utility District for evacuation plans
72 | Coordinate with GCECG on amateur radio support (embed in other EOCs)
72 | Evaluate and determine EOC Readiness Level
72 | GCOEM news conference; prepare Blackboard messages and schedule based on phased evacuation
72 | Initiate EOC building security
72 | Make final evacuation decisions
72 | Notify county employees of shutdown of county facilities
72 | Notify public of evacuation plan, in phases by zip codes as warranted; utilize Blackboard and multi-media
72 | Notify public of possible health screening at embarkation and shelter locations
72 | Notify regional partners of evacuation timeline.
72 | Notify TDEM of evacuation timeline and shelter needs
72 | Release staff to prepare homes/families in advance of general evacuation notice
72 | Set up Call Center with approved Frequently Asked Questions
72 | Traffic Management Plan activated by DPS/TxDOT
72 | Work with media and other partners to publicize evacuation plan
60 | Assist jurisdictions with transport of functional/medical needs residents to points of embarkation
60 | Assist GCSO, DPS and jurisdictions with evacuation along priority evacuation routes I-45, Hwy 6, Hwy 146
60 | Begin evacuation of Bolivar Peninsula and low-lying areas; coordinate with partners and media
60 | Continue monitoring arrival/status of medical needs residents in San Antonio
60 | Continue moving equipment and personnel to Santa Fe High School
60 | Coordinate with school and city officials on potential opening of refuges of last resort
60 | Coordinate with state on placement of IMT and SAR teams
60 | Load buses at embarkation points and send to Austin shelter hub for assignment to shelters
60 | Monitor bus evacuation routes for issues/problems; track locations of all wristband evacuees
60 | Update Incident Action Plan as needed
60 | Utilize web sites, social media, mass notification and other means to notify public of potential threat
60 | Verify all medical/functional needs residents are en route to shelters; verify TDEM has necessary information
48 | Complete all bus loading activities at points of embarkation; retain busses for final run
48 | Conduct final conference call with county departments
48 | Continue evacuation of Island and Mainland in phases
48 | Coordinate bunk assignments and next EOC shift plan
48 | Coordinate final bus pickup across mainland; utilize remaining busses and ensure EOC receives final manifests
48 | Coordinate with TxDOT regarding ferry service to/from Bolivar Peninsula (45 mph wind or 4.5’ tides)
48 | Finalize EOC staffing plan for initial shifts
48 | Relocate equipment/vehicles to safer locations around EOC; secure loose items around GCOEM
48 | Send final messages and conduct final sweeps of Bolivar Peninsula and other low-lying areas to ensure all threatened residents have left; assist those still unable to leave on their own
36 | Complete evacuation of all or portions of county as directed by county judge and mayors
36 | Notify public of conclusion of evacuation and switch to Shelter in Place messages
36 | Notify state, regional and local partners of completion of evacuation
36 | Update Incident Action Plan for next shift
24 | Verify all ride-out teams are secure at Santa Fe High School and other county locations
12 | Complete final activities prior to onset of 39 mph winds
12 | Coordinate with state on potential POD and DRC locations

## RESPONSIBLE PARTY
Responsible Party | Add any names to the list in column A that you would like to have in your Responsible Party drop down list on the Task List.
Example 1
Example 2
Example 3
Example 4
Example 5

## HOUR
COMPLETION HOUR
12
24
36
48
60
72
84
96
108
120