## TASK LIST
Hour | Activities | Responsible Party | Completed
12 | Conduct initial damage assessments and report findings
12 | Establish initial incident objectives and priorities for the operational period
12 | Confirm safety of all response personnel and conduct personnel accountability
12 | Initiate search and rescue operations as needed
12 | Provide public information updates regarding safety, curfews, and ongoing response efforts
24 | Conduct detailed damage assessments and begin documentation
24 | Begin debris clearance on primary roads and critical infrastructure
24 | Assess and restore critical utilities and infrastructure (power, water, communications)
24 | Establish and staff shelters for displaced residents
24 | Coordinate with healthcare facilities to ensure continuity of care for patients
24 | Provide food, water, and other essential supplies to affected populations
24 | Continue public information updates and provide information on available resources
36 | Continue search and rescue operations as needed
36 | Conduct secondary damage assessments and update situation reports
36 | Prioritize and begin repairs on critical infrastructure
36 | Coordinate with state and federal agencies for additional resources and support
36 | Establish points of distribution (PODs) for essential supplies
36 | Begin preliminary damage assessments for potential federal assistance
36 | Provide mental health and crisis counseling services to affected populations
36 | Implement initial recovery operations and planning
48 | Continue debris clearance and infrastructure repairs
48 | Conduct community outreach and support services
48 | Begin environmental health assessments (water quality, hazardous materials, etc.)
48 | Coordinate with non-governmental organizations (NGOs) for additional support
48 | Provide detailed public information updates and recovery resources
48 | Implement curfews and security measures as needed to protect public safety
48 | Establish temporary housing solutions for displaced residents
48 | Begin assessment and restoration of public transportation systems
60 | Continue damage assessments and documentation for insurance and federal assistance
60 | Monitor and support healthcare facilities and services
60 | Begin restoration of government and community services
60 | Coordinate volunteer and donation management
60 | Assess and address needs of vulnerable populations (elderly, disabled, etc.)
60 | Provide ongoing public information and community meetings for updates
60 | Implement long-term recovery planning and coordination with stakeholders
60 | Conduct regular briefings with response teams and partner agencies
72 | Continue infrastructure repairs and debris removal
72 | Conduct thorough environmental and public health assessments
72 | Provide ongoing support for displaced residents and temporary housing
72 | Begin economic recovery assessments and support for local businesses
72 | Coordinate with educational institutions for reopening plans
72 | Provide ongoing mental health and crisis counseling services
72 | Develop and implement plans for long-term recovery and rebuilding
72 | Conduct after-action reviews and update response plans as needed
84 | Continue public and environmental health assessments and mitigations
84 | Restore full operations of critical infrastructure and utilities
84 | Provide ongoing community support and recovery services
84 | Continue detailed damage assessments and documentation for recovery funding
84 | Coordinate long-term housing solutions for displaced residents
84 | Implement plans for rebuilding and reconstruction
84 | Engage with community stakeholders for recovery planning and support
84 | Conduct regular community updates and public information briefings
96 | Ensure ongoing support for healthcare facilities and services
96 | Continue monitoring and addressing needs of vulnerable populations
96 | Conduct regular coordination meetings with response and recovery agencies
96 | Provide comprehensive public information and recovery resource updates
96 | Begin assessment and recovery of cultural and historical sites
96 | Implement economic recovery initiatives and support for local businesses
96 | Develop and implement mitigation strategies to prevent future disasters
96 | Continue after-action reviews and incorporate lessons learned into future plans
108 | Complete remaining infrastructure repairs and debris removal
108 | Transition from response to full recovery operations
108 | Provide long-term mental health and social services to affected populations
108 | Ensure all displaced residents have access to temporary or permanent housing
108 | Coordinate ongoing recovery efforts with state and federal agencies
108 | Implement plans for community rebuilding and resilience
108 | Conduct final after-action reviews and document best practices
108 | Develop and update comprehensive emergency response and recovery plans
120 | Finalize and document all damage assessments and recovery efforts
120 | Ensure full restoration of government and community services
120 | Complete the transition to long-term recovery and rebuilding operations
120 | Conduct final public information updates and community meetings
120 | Begin planning for future disaster preparedness and mitigation efforts
120 | Celebrate community resilience and recovery achievements
120 | Recognize and thank all response and recovery personnel and volunteers
120 | Develop and distribute final after-action reports and recommendations

## RESPONSIBLE PARTY
Responsible Party | Add any names to the list in column A that you would like to have in your Responsible Party drop down list on the Task List.
Example 1
Example 2
Example 3
Example 4
Example 5

## HOUR
COMPLETION HOUR
12
24
36
48
60
72
84
96
108
120